## Rebrand Project Plan
|  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
| Description | Primary Resource | Target Delivery Date | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | Launch
Rebranding
Analysis of Who We Are
x | 1:1 Introductions | Danielle | 2020-05-08 | bar: May 1
x | Baseline Data Analysis | Danielle | 2020-05-05 | bar: May 1 to May 2
| Select Customer Conversations/Research | Danielle | 2020-05-22 | bar: May 2 to May 3
x | Internal Meeting (Offsite if possible) | Team | 2020-05-12 | bar: May 2
Branding Selection
| Brand Name Finalists (if changing) | Team | 2020-05-15 | bar: May 2
| Core Value Principle Delivery | Team | 2020-05-19 | bar: May 2
| Messaging Principles Options/Delivery | Team | 2020-05-21 | bar: May 2
| Name Selection (if changing) | Team | 2020-05-21 | bar: May 3
| Logo Concepts and Selection | Team | 2020-05-29 | bar: May 4
| Finalize Logo | ND, DW | 2020-06-05 | bar: June 1
| Who We Are Statement | Danielle | 2020-06-05 | bar: June 1
Strategy and Delivery Selection
x | Site Navigation Selection with Keywords | Danielle | 2020-05-15 | bar: May 2
x | Customer Collateral Selection | Team | 2020-05-21 | bar: May 2
x | Internal / Channel Enablement Selection | Team | 2020-05-21 | bar: May 2
| Outline Product Sheet, Battlecard, Overview, Product Deck Section, Product Site Page | ND, DW | May 20 2020 | bar: May 3
| THE BOOK: Create Templated Product Resource | Nicolette | July 15 2020 | bar: May 4 to June 2
| Access Clean WP - Yoast, cache, ssl, gtm, GA, chat, hubspot | Web Developer | May 30 2020 | bar: May 4 to June 1
| Wireframe Site Legos + Mobile | Web Developer | May 30 2020 | bar: May 3 to May 4
| Write Site Pages w/ meta data, alt tags | ND, DW | June | bar: June 1 to June 4
| Wireframe Home Page | Web Developer | July 10 2020 | bar: July 2
| Implement Marketing Tool (Hubspot, Pardot, Marketo) | Danielle | July 15 2020 | bar: July 1 to July 3
Site & Collateral Build
| Design Site Legos | Web Developer | 2020-06-10 | bar: June 2 to June 3
| Design Navigation and Footer | Web Developer | 2020-06-01 | bar: June 1
| Design Product Sheet, Battlecard, Overview | Nicolette | July 1 2020 | bar: July 1
| Image Selection | ND, DW | July | bar: July 3 to July 4
| Build Site | Web Developer | July | bar: June 4 to July 4
| Design Home Page | ND, DW | Aug 1 2020 | bar: July 4 to August 1
| Build Home Page | Web Developer | Aug 7 2020 | bar: July 4 to August 1
| Build CTA and forms - tag tracking and ga events | Web Developer | Aug 7 2020 | bar: July 4 to August 1
| Build Collateral/ Input Content | ND, DW | July | bar: August 1 to August 2
| Build/Design Corp Deck | ND, DW | July 20 2020 | bar: July 4
| Messaging Guide | Danielle | May 30 2020 | bar: May 4
| Branding Guide - Logo/font pack | ND, DW | July 19 2020 | bar: July 3
| PR Prep and Boiler Plate | ND, DW | July 30 2020 | bar: July 4
Extended Digital Presence Prep
| Social Copy and Image Prep | Nicolette | 2020-07-25
| External Communications Prep (Lists, Emails, Templates) | ND, DW | 2020-07-25
| Campaign in a Box Build | ND, DW | 2020-08-17 | bar: August 3
Testing and Feeback
| Final Editing | ND, DW | 2020-08-01 | bar: August 1 to August 2
| Internal Team Preview ¦ Team Editing Suggestions | ND, DW | 2020-08-01 | bar: August 1
| Prep Redirect List | ND, DW | 2020-08-01 | bar: August 1
| Marketing Final Test | ND, DW | 2020-08-01 | bar: August 3
Launch
| Site Release | ND, DW | 2020-08-20
| Social Site Updates | ND, DW | Launch
| redirects and site maps | Danielle | Launch
| Tracking Testing Confirmation and Report Set Up | Danielle | 2020-08-13
| Tier 1 Directory Updates | Nicolette | Launch
Post Brand Launch
| Message Training and Certification | Danielle | 2020-08-13
| SEO Audit | Danielle | Launch
| Launch Paid Ads / Media Strategy | Danielle | Launch
| Vendor / Technology Relationship Build, MDF | Nicolette | Launch
Data Integrity
Data Analysis
| Analysis | Danielle
| Stakeholder Summary Review of Funnel | Danielle
| Funnel Stage Map | Danielle
| Change Recommendations for All Objects | Danielle
| Implementation | Danielle
| Reporting Setup Phase 1 | Danielle
| Tracking / Field Capture on Form Set Up | Danielle
| Campaign Code Historicals (ie: webform to campaign code | Danielle
| Campaign Code Workflows of First Touch. Last Touch Sourcing | Danielle
| Duplicate Contacts Clean Up | Danielle
| Cleaning Junk in database | Danielle
| Past List Import | Danielle
| Tattletale Reporting | Danielle
| Source Funnel and Campaign Code Report Set Up | Danielle
Phase II Brand / Website
| Blog or Knowledge Base Design and Content Contribution | Nicolette | Post
| Managed Services Customer Collateral | Nicolette | Post
| DC Locations Webpages | Nicolette | Post
| Customer / Use Case collateral / site incorporation | ND, DW | Post
| Chat Playbooks / routing | Danielle | Post
| Tier 2 Directory Updates | Nicolette | Post
Camapaign Builds
| Business Continuity Campaign | Danielle | Post
| VMware Expert Campagin | Danielle | Post
| Brand/Value Campaign | Danielle | Post